## General
Task_Id | Title | Description | Status
1 | Create Excel sheet for backlog | Create an excel sheet for tracking the backlog of the project | DONE
2 | Create Git Repository | Create the github repository for version of control | DONE

## Frontend
Task_Id | Title | Description | Status
1 | [Frontend-1] Create the angular project | Create an angular project that will serve as UI for the ticketing system | DONE
2 | [Frontend-2] Create a Login page | Create a login page that contains a form with email, password and a submit button. The login page should also have a redirect button to the register page | DONE
3 | [Frontend-3] Create a Register page | Create a register page that contains a form with email, password, confirm password, first name, last name, a submit button. The page should have a redirect button to the login page | DONE
4 | [Frontend-4] Create the login page logic | Create the logic behind the login page, the request to the identity api and the user session | DONE
5 | [Frontend-5] Create the register page logic | Create the logic behind the register page, the request to the identity api | DONE
6 | [Frontend-6]Create the display of the tickets for a specific user | Create the display as a table for the existing tickets for a specific user | DONE
7 | [Frontend-7] Add the frontend project to the docker-compose | Add the frontend project to the docker compose so that it will create a container with the project in the same network as the apis
8 | [Frontend-8] Create the delete and close buttons and functionalities | Create buttons for each ticket so that you can close or delete them | DONE
9 | [Frontend-9] Create the create ticket page | Create the create ticket page and functionality | DONE
10 | [Frontend-10] Create edit page | Create the edit page functionality

## Backend
Task_Id | Title | Description | Status
1 | [SPIKE] Monolith or microservices? | Investigate what to chose between monolith or microservices architecture | DONE
2 | [Identity-1]Create Identity API Project | Create a .net core project API that will handle the authentication for users | DONE
3 | [Identity-2]Create the user model | Create a user model that contains Id, name, email, password | DONE
4 | [Identity-3]Create all required projects | Create the DataAccess and Application projects for the Identity Microservice and install the nuget packages for authorization, entity framework and jwt | DONE
5 | [Identity-4]Configure the Identity API Startup | Configure the project startup to contain swagger, authentication, controllers | DONE
6 | [Identity-5]Establish connection with the database | Create the DB Context and add the configuration into the startup project, create the migrations and establish the connection string | DONE
7 | [Identity-6]Add Docker compose project | Add the docker-compose project that contains the Identity Api image and a mssql database | DONE
8 | [Identity-7]Add Identity Repository and controller logic for register | Create the identity repository and controller that contains register logic | DONE
9 | [Identity-8]Add login endpoint | Create the endpoint that contains login logic | DONE
10 | [Ticket-1] Create Tickets API Project | Create a .net core projectAPI that will handle the tickets for users | DONE
11 | [Ticket-2] Create the required projects | Create the required projects that will have the same structure as Identity microservice | DONE
12 | [Ticket-3] Create the models | Create all the models that are needed for the ticketing system that reflect the requirements. | DONE
13 | [Ticket-4] Configure the Ticket API Startup | Configure the project startup to contain swagger, authentication, controllers | DONE
14 | [Ticket-5] Add the project to the docker-compose | Modify docker-compose to run the Tickets API together with the other containers | DONE
15 | [Ticket-7] Establish connection with the database | Create the DB Context and add the configuration into the startup project, create the migrations and establish the connection string | DONE
16 | [Ticket-6] Add tests for creating tickets | In order to respect the TDD method, implement tests for tickets | INCOMPLETE
17 | [Ticket-8] Implement functionality for creating tickets | Implement functionality for creating tickets so that all the tests will pass | DONE
18 | [Ticket-9] Add test and functionality for update and delete tickets | Implement tests for update and delete and the functionality so that all the tests are passing | INCOMPLETE
19 | [Ticket-10] Create endpoints that reflect CRUD for tickets | Implement endpoints in the tickets controller so that it will reflect the CRUD operations | DONE
20 | [Ticket-11] Create default values | Create default values to be added into the database | DONE
21 | [Ticket-12] Create close ticket logic and endpoint | Create the logic and endpoint for closing a ticket, a ticket is close when the closed field is populated, it will be populated with the date in that moment. | DONE
22 | [Ticket-13] Create endpoint for standard properties for tickets | create a get endpoint for getting standard values from db for status, priority, etc. | DONE
23 | [Ticket-14] Create endpoint and logic for getting tickets for user | Create an endpoint and logic to get tickets for a specific user | DONE
24 | [Identity-9] Create a check session endpoint | Create an endpoint that checks if the session is still available | DONE